## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME
PROJECT ID | 2982
PROJECT MANAGER | Jayanth G S
DOCUMENT VERSION
PROJECT START DATE | 15th June 2020
PROJECT END DATE | 31st July 2020
SL NO | FEATURE NAME | VERSION 1 LINK | VERSION 1 CREATION DATE | VERSION 2 LINK | VERSION 2 CREATION DATE | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | SDLC | Project Methodology | 23rd June 2020 | Not Changed | Not Changed | Understanding IP- Project Methodology | Completed
2 | Problem Statement | DS problem statement | 26th June 2020 | DS problem statement | 28th June 2020 | Understanding problem statement | Completed
3 | Section 2 doubts | DS problem statement | 28th June 2020 | FAQs | 29th June 2020 | Cleared doubts with the FAQs | Completed
4 | Downloadable resources | Link not working | 2nd July 2020 | New link generated | 2nd July 2020 | Resources are dowoadable | Completed
5 | Week 2 tasks | SRS, Project Charter | 6th July 2020 | Not Changed | 6th July 2020 | Updating the excel files | Ongoing
6 | Project Plan | Excel files regarding plans & reference | 17th July 2020 | Not Changed | 17th July 2020 | Excel files demonstrating all the procedure | Ongoing
7 | Development Log | Updating documents | 20th July 2020 | Changing specifications | 24th July 2020 | Software and updating visulaization | Ongoing
8 | RAID Log Updation | Reviewing all the documents | 28th July 2020 | Changing specifications | 29th July 2020 | Updating the final project report | Ongoing
9 | Submission Link | GitHub Procedure provided | 30th July 2020 | Link demonstartion given | 31st July 2020 | Project Submitted with all external files | Ongoing