## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-07-06
PROJECT DELIVERABLE | GitHub |  | EXECUTION PHASE END DATE: |  | 2020-07-31
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | Completed
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Initiation | Identify the problem statement |  | 2020-06-23 | 2020-06-23
| Create project charter |  | 2020-06-25 | 2020-06-26
| Requirment gathering |  | 2020-06-27 | 2020-06-27
| understanding the dataset |  | 2020-06-28 | 2020-06-28
2. Planning | Project plan |  | 2020-07-02 | 2020-07-03
| Project procedure |  | 2020-07-04 | 2020-07-06
| Work distribution |  | 2020-07-07 | 2020-07-07
3. Execution | Procedure finalization |  | 2020-07-10 | 2020-07-11
| Build the project |  | 2020-07-12 | 2020-07-13
4. Compilation | Reading the dataset |  | 2020-07-15 | 2020-07-15
| Data Pre-processing |  | 2020-07-16 | 2020-07-16
| Null Value counts |  | 2020-07-16 | 2020-07-16
| Determination of missing values |  | 2020-07-17 | 2020-07-17
| Determination of percentage of missing values |  | 2020-07-17 | 2020-07-18
| Plotting of those missing values |  | 2020-07-20 | 2020-07-22
5. Visualization | Understanding the problem statement |  | 2020-07-23 | 2020-07-23
| Solving the statements with each graphical reoresentation |  | 2020-07-23 | 2020-07-27
6. Classifier | Solving the target variable as classifier model |  | 2020-07-28 | 2020-07-28
7. Testing | Manual Testing |  | 2020-07-29 | 2020-07-30
| Software Testing |  | 2020-07-30 | 2020-07-31
8. Closure | Final Testing & closing of project |  | 2020-07-31 | 2020-07-31